## Slide 1: Engineering Management
University of Mustansiriyah 2019-2020
College of Engineering 3rd Stage
High. & Trans Eng. Dep.
Lecture No.17: Programming Techniques, Programming Evaluation and Review Technique, Example 1 (part 1)
Lecturers: Dr. Ali Jabbar
Dr. Abeer K. Jameel

## Slide 3
Activity | Duration (week) |  |  | Depend on
 | t0 | tm | tp | 
A | 6 | 9 | 12 | -
B | 6 | 8 | 10 | A
C | 2 | 5 | 8 | -
D | 4 | 7 | 10 | C
E | 4 | 6 | 8 | D
F | 5 | 9 | 13 | D
G | 2 | 3 | 4 | F
H | 1 | 2 | 3 | B,E
I | 2 | 3 | 4 | G,H
J | 2 | 4 | 6 | B
K | 3 | 4 | 5 | J
L | 2 | 3 | 4 | K,I

## Slide 4
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 
B | 6 | 8 | 10 | A | 
C | 2 | 5 | 8 | - | 
D | 4 | 7 | 10 | C | 
E | 4 | 6 | 8 | D | 
F | 5 | 9 | 13 | D | 
G | 2 | 3 | 4 | F | 
H | 1 | 2 | 3 | B,E | 
I | 2 | 3 | 4 | G,H | 
J | 2 | 4 | 6 | B | 
K | 3 | 4 | 5 | J | 
L | 2 | 3 | 4 | K,I | 
te(A)=(6+4(9)+12)/6

## Slide 5
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 
C | 2 | 5 | 8 | - | 
D | 4 | 7 | 10 | C | 
E | 4 | 6 | 8 | D | 
F | 5 | 9 | 13 | D | 
G | 2 | 3 | 4 | F | 
H | 1 | 2 | 3 | B,E | 
I | 2 | 3 | 4 | G,H | 
J | 2 | 4 | 6 | B | 
K | 3 | 4 | 5 | J | 
L | 2 | 3 | 4 | K,I | 
te(A)=(6+4(9)+12)/6

## Slide 6
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 
C | 2 | 5 | 8 | - | 
D | 4 | 7 | 10 | C | 
E | 4 | 6 | 8 | D | 
F | 5 | 9 | 13 | D | 
G | 2 | 3 | 4 | F | 
H | 1 | 2 | 3 | B,E | 
I | 2 | 3 | 4 | G,H | 
J | 2 | 4 | 6 | B | 
K | 3 | 4 | 5 | J | 
L | 2 | 3 | 4 | K,I | 
te(A)=(6+4(9)+12)/6=9
te(B)=(6+4(8)+10)/6=

## Slide 7
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 
D | 4 | 7 | 10 | C | 
E | 4 | 6 | 8 | D | 
F | 5 | 9 | 13 | D | 
G | 2 | 3 | 4 | F | 
H | 1 | 2 | 3 | B,E | 
I | 2 | 3 | 4 | G,H | 
J | 2 | 4 | 6 | B | 
K | 3 | 4 | 5 | J | 
L | 2 | 3 | 4 | K,I | 
te(A)=(6+4(9)+12)/6=9
te(B)=(6+4(8)+10)/6=8

## Slide 8
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3

## Slide 9
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
8
3
G
9
2
H

## Slide 10
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
8
3
G
9
2
H

## Slide 11
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
7
E
6
F
9
8
3
G
9
2
H

## Slide 12
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
8
3
G
9
2
H

## Slide 13
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
8
3
G
9
2
H
8
J
4

## Slide 14
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11

## Slide 15
Activity | Duration (week) |  |  | Depend on | te
 | t0 | tm | tp |  | 
A | 6 | 9 | 12 | - | 9
B | 6 | 8 | 10 | A | 8
C | 2 | 5 | 8 | - | 5
D | 4 | 7 | 10 | C | 7
E | 4 | 6 | 8 | D | 6
F | 5 | 9 | 13 | D | 9
G | 2 | 3 | 4 | F | 3
H | 1 | 2 | 3 | B,E | 2
I | 2 | 3 | 4 | G,H | 3
J | 2 | 4 | 6 | B | 4
K | 3 | 4 | 5 | J | 4
L | 2 | 3 | 4 | K,I | 3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 16
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 |  |  | 
B | 6 | 8 | 10 | 8 |  |  |  | 
C | 2 | 5 | 8 | 5 | 0 |  |  | 
D | 4 | 7 | 10 | 7 |  |  |  | 
E | 4 | 6 | 8 | 6 |  |  |  | 
F | 5 | 9 | 13 | 9 |  |  |  | 
G | 2 | 3 | 4 | 3 |  |  |  | 
H | 1 | 2 | 3 | 2 |  |  |  | 
I | 2 | 3 | 4 | 3 |  |  |  | 
J | 2 | 4 | 6 | 4 |  |  |  | 
K | 3 | 4 | 5 | 4 |  |  |  | 
L | 2 | 3 | 4 | 3 |  |  |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 17
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 |  |  |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 |  |  |  | 
E | 4 | 6 | 8 | 6 |  |  |  | 
F | 5 | 9 | 13 | 9 |  |  |  | 
G | 2 | 3 | 4 | 3 |  |  |  | 
H | 1 | 2 | 3 | 2 |  |  |  | 
I | 2 | 3 | 4 | 3 |  |  |  | 
J | 2 | 4 | 6 | 4 |  |  |  | 
K | 3 | 4 | 5 | 4 |  |  |  | 
L | 2 | 3 | 4 | 3 |  |  |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 18
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 |  |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 |  |  |  | 
E | 4 | 6 | 8 | 6 |  |  |  | 
F | 5 | 9 | 13 | 9 |  |  |  | 
G | 2 | 3 | 4 | 3 |  |  |  | 
H | 1 | 2 | 3 | 2 |  |  |  | 
I | 2 | 3 | 4 | 3 |  |  |  | 
J | 2 | 4 | 6 | 4 |  |  |  | 
K | 3 | 4 | 5 | 4 |  |  |  | 
L | 2 | 3 | 4 | 3 |  |  |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 19
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 |  |  |  | 
E | 4 | 6 | 8 | 6 |  |  |  | 
F | 5 | 9 | 13 | 9 |  |  |  | 
G | 2 | 3 | 4 | 3 |  |  |  | 
H | 1 | 2 | 3 | 2 |  |  |  | 
I | 2 | 3 | 4 | 3 |  |  |  | 
J | 2 | 4 | 6 | 4 |  |  |  | 
K | 3 | 4 | 5 | 4 |  |  |  | 
L | 2 | 3 | 4 | 3 |  |  |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 20
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 |  |  |  | 
I | 2 | 3 | 4 | 3 |  |  |  | 
J | 2 | 4 | 6 | 4 |  |  |  | 
K | 3 | 4 | 5 | 4 |  |  |  | 
L | 2 | 3 | 4 | 3 |  |  |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 21
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I | 2 | 3 | 4 | 3 |  |  |  | 
J | 2 | 4 | 6 | 4 |  |  |  | 
K | 3 | 4 | 5 | 4 |  |  |  | 
L | 2 | 3 | 4 | 3 |  |  |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 22
Activity | Duration (week) |  |  | te | Es | Ef |  | 
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I | 2 | 3 | 4 | 3 | 24 | 27 |  | 
J | 2 | 4 | 6 | 4 | 17 | 21 |  | 
K | 3 | 4 | 5 | 4 | 21 | 25 |  | 
L | 2 | 3 | 4 | 3 | 27 | 30 |  | 
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 23
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I | 2 | 3 | 4 | 3 | 24 | 27 |  | 
J | 2 | 4 | 6 | 4 | 17 | 21 |  | 
K | 3 | 4 | 5 | 4 | 21 | 25 |  | 
L | 2 | 3 | 4 | 3 | 27 | 30 |  | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 24
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I | 2 | 3 | 4 | 3 | 24 | 27 |  | 
J | 2 | 4 | 6 | 4 | 17 | 21 |  | 
K | 3 | 4 | 5 | 4 | 21 | 25 |  | 
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 25
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I | 2 | 3 | 4 | 3 | 24 | 27 |  | 27
J | 2 | 4 | 6 | 4 | 17 | 21 |  | 
K | 3 | 4 | 5 | 4 | 21 | 25 |  | 27
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 26
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27
J | 2 | 4 | 6 | 4 | 17 | 21 |  | 
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 27
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 |  | 
F | 5 | 9 | 13 | 9 | 12 | 21 |  | 
G | 2 | 3 | 4 | 3 | 21 | 24 |  | 
H | 1 | 2 | 3 | 2 | 18 | 20 |  | 
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 28
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D | 4 | 7 | 10 | 7 | 5 | 12 |  | 
E | 4 | 6 | 8 | 6 | 12 | 18 | 16 | 22
F* | 5 | 9 | 13 | 9 | 12 | 21 | 12 | 21
G* | 2 | 3 | 4 | 3 | 21 | 24 | 21 | 24
H | 1 | 2 | 3 | 2 | 18 | 20 | 22 | 24
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 29
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 |  | 
B | 6 | 8 | 10 | 8 | 9 | 17 |  | 
C | 2 | 5 | 8 | 5 | 0 | 5 |  | 
D* | 4 | 7 | 10 | 7 | 5 | 12 | 5 | 12
E | 4 | 6 | 8 | 6 | 12 | 18 | 16 | 22
F* | 5 | 9 | 13 | 9 | 12 | 21 | 12 | 21
G* | 2 | 3 | 4 | 3 | 21 | 24 | 21 | 24
H | 1 | 2 | 3 | 2 | 18 | 20 | 22 | 24
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 30
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf
 | t0 | tm | tp |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 | 2 | 11
B | 6 | 8 | 10 | 8 | 9 | 17 | 11 | 19
C* | 2 | 5 | 8 | 5 | 0 | 5 | 0 | 5
D* | 4 | 7 | 10 | 7 | 5 | 12 | 5 | 12
E | 4 | 6 | 8 | 6 | 12 | 18 | 16 | 22
F* | 5 | 9 | 13 | 9 | 12 | 21 | 12 | 21
G* | 2 | 3 | 4 | 3 | 21 | 24 | 21 | 24
H | 1 | 2 | 3 | 2 | 18 | 20 | 22 | 24
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 31
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | TF
 | t0 | tm | tp |  |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 | 2 | 11 | 2
B | 6 | 8 | 10 | 8 | 9 | 17 | 11 | 19 | 2
C* | 2 | 5 | 8 | 5 | 0 | 5 | 0 | 5 | 0
D* | 4 | 7 | 10 | 7 | 5 | 12 | 5 | 12 | 0
E | 4 | 6 | 8 | 6 | 12 | 18 | 16 | 22 | 4
F* | 5 | 9 | 13 | 9 | 12 | 21 | 12 | 21 | 0
G* | 2 | 3 | 4 | 3 | 21 | 24 | 21 | 24 | 0
H | 1 | 2 | 3 | 2 | 18 | 20 | 22 | 24 | 4
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27 | 0
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23 | 2
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27 | 2
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30 | 0
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 32
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | TF | S
 | t0 | tm | tp |  |  |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 | 2 | 11 | 2 | 
B | 6 | 8 | 10 | 8 | 9 | 17 | 11 | 19 | 2 | 
C* | 2 | 5 | 8 | 5 | 0 | 5 | 0 | 5 | 0 | 1
D* | 4 | 7 | 10 | 7 | 5 | 12 | 5 | 12 | 0 | 1
E | 4 | 6 | 8 | 6 | 12 | 18 | 16 | 22 | 4 | 
F* | 5 | 9 | 13 | 9 | 12 | 21 | 12 | 21 | 0 | 4/3
G* | 2 | 3 | 4 | 3 | 21 | 24 | 21 | 24 | 0 | 1/3
H | 1 | 2 | 3 | 2 | 18 | 20 | 22 | 24 | 4 | 
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27 | 0 | 1/3
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23 | 2 | 
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27 | 2 | 
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30 | 0 | 1/3
1
3
2
A
C
9
5
4
B
8
5
D
7
6
7
E
6
F
9
3
G
9
2
H
8
J
4
I
3
11
3
12
L
4
K

## Slide 33
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | TF | S
 | t0 | tm | tp |  |  |  |  |  |  | 
A | 6 | 9 | 12 | 9 | 0 | 9 | 2 | 11 | 2 | 
B | 6 | 8 | 10 | 8 | 9 | 17 | 11 | 19 | 2 | 
C* | 2 | 5 | 8 | 5 | 0 | 5 | 0 | 5 | 0 | 1
D* | 4 | 7 | 10 | 7 | 5 | 12 | 5 | 12 | 0 | 1
E | 4 | 6 | 8 | 6 | 12 | 18 | 16 | 22 | 4 | 
F* | 5 | 9 | 13 | 9 | 12 | 21 | 12 | 21 | 0 | 4/3
G* | 2 | 3 | 4 | 3 | 21 | 24 | 21 | 24 | 0 | 1/3
H | 1 | 2 | 3 | 2 | 18 | 20 | 22 | 24 | 4 | 
I* | 2 | 3 | 4 | 3 | 24 | 27 | 24 | 27 | 0 | 1/3
J | 2 | 4 | 6 | 4 | 17 | 21 | 19 | 23 | 2 | 
K | 3 | 4 | 5 | 4 | 21 | 25 | 23 | 27 | 2 | 
L* | 2 | 3 | 4 | 3 | 27 | 30 | 27 | 30 | 0 | 1/3