## Slide 1: Engineering Management
University of Mustansiriyah 2019-2020
College of Engineering 3rd Stage
High. & Trans Eng. Dep.
Lecture No.17: Programming Techniques, Programming Evaluation and Review Technique PERT, Example 3
Lecturers: Dr. Ali Jabbar
Dr. Abeer K. Jameel

## Slide 3
Activity | Duration (week) |  | 
 | to | tm | tp
1-2 | 4 | 5 | 6
1-3 | 1 | 3 | 5
2-4 | 2 | 2 | 2
2-5 | 3 | 4 | 5
3-7 | 7 | 8 | 15
4-5 | 1 | 2 | 3
5-6 | 1 | 1 | 1
6-7 | 6 | 6 | 12
7-8 | 1 | 2 | 3
Solution

## Slide 4
Solution
Activity | Duration (week) |  |  | te
 | to | tm | tp | 
1-2 | 4 | 5 | 6 | 
1-3 | 1 | 3 | 5 | 
2-4 | 2 | 2 | 2 | 
2-5 | 3 | 4 | 5 | 
3-7 | 7 | 8 | 15 | 
4-5 | 1 | 2 | 3 | 
5-6 | 1 | 1 | 1 | 
6-7 | 6 | 6 | 12 | 
7-8 | 1 | 2 | 3 | 

## Slide 5
Solution
Activity | Duration (week) |  |  | te
 | to | tm | tp | 
1-2 | 4 | 5 | 6 | 5
1-3 | 1 | 3 | 5 | 3
2-4 | 2 | 2 | 2 | 2
2-5 | 3 | 4 | 5 | 4
3-7 | 7 | 8 | 15 | 10
4-5 | 1 | 2 | 3 | 2
5-6 | 1 | 1 | 1 | 1
6-7 | 6 | 6 | 12 | 7
7-8 | 1 | 2 | 3 | 2

## Slide 6
Solution
Activity | Duration (week) |  |  | te
 | to | tm | tp | 
1-2 | 4 | 5 | 6 | 5
1-3 | 1 | 3 | 5 | 3
2-4 | 2 | 2 | 2 | 2
2-5 | 3 | 4 | 5 | 4
3-7 | 7 | 8 | 15 | 9
4-5 | 1 | 2 | 3 | 2
5-6 | 1 | 1 | 1 | 1
6-7 | 6 | 6 | 12 | 7
7-8 | 1 | 2 | 3 | 2
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2

## Slide 7
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 |  |  |  |  | 
1-3 | 1 | 3 | 5 | 3 |  |  |  |  | 
2-4 | 2 | 2 | 2 | 2 |  |  |  |  | 
2-5 | 3 | 4 | 5 | 4 |  |  |  |  | 
3-7 | 7 | 8 | 15 | 9 |  |  |  |  | 
4-5 | 1 | 2 | 3 | 2 |  |  |  |  | 
5-6 | 1 | 1 | 1 | 1 |  |  |  |  | 
6-7 | 6 | 6 | 12 | 7 |  |  |  |  | 
7-8 | 1 | 2 | 3 | 2 |  |  |  |  | 

## Slide 8
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 |  |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 |  |  |  | 
2-4 | 2 | 2 | 2 | 2 |  |  |  |  | 
2-5 | 3 | 4 | 5 | 4 |  |  |  |  | 
3-7 | 7 | 8 | 15 | 9 |  |  |  |  | 
4-5 | 1 | 2 | 3 | 2 |  |  |  |  | 
5-6 | 1 | 1 | 1 | 1 |  |  |  |  | 
6-7 | 6 | 6 | 12 | 7 |  |  |  |  | 
7-8 | 1 | 2 | 3 | 2 |  |  |  |  | 

## Slide 9
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 |  |  |  |  | 
2-5 | 3 | 4 | 5 | 4 |  |  |  |  | 
3-7 | 7 | 8 | 15 | 9 |  |  |  |  | 
4-5 | 1 | 2 | 3 | 2 |  |  |  |  | 
5-6 | 1 | 1 | 1 | 1 |  |  |  |  | 
6-7 | 6 | 6 | 12 | 7 |  |  |  |  | 
7-8 | 1 | 2 | 3 | 2 |  |  |  |  | 

## Slide 10
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 | 5 | 7 |  |  | 
2-5 | 3 | 4 | 5 | 4 | 5 | 9 |  |  | 
3-7 | 7 | 8 | 15 | 9 |  |  |  |  | 
4-5 | 1 | 2 | 3 | 2 |  |  |  |  | 
5-6 | 1 | 1 | 1 | 1 |  |  |  |  | 
6-7 | 6 | 6 | 12 | 7 |  |  |  |  | 
7-8 | 1 | 2 | 3 | 2 |  |  |  |  | 

## Slide 11
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 | 5 | 7 |  |  | 
2-5 | 3 | 4 | 5 | 4 | 5 | 9 |  |  | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 |  |  | 
4-5 | 1 | 2 | 3 | 2 |  |  |  |  | 
5-6 | 1 | 1 | 1 | 1 |  |  |  |  | 
6-7 | 6 | 6 | 12 | 7 |  |  |  |  | 
7-8 | 1 | 2 | 3 | 2 |  |  |  |  | 

## Slide 12
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 | 5 | 7 |  |  | 
2-5 | 3 | 4 | 5 | 4 | 5 | 9 |  |  | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 |  |  | 
4-5 | 1 | 2 | 3 | 2 | 7 | 9 |  |  | 
5-6 | 1 | 1 | 1 | 1 |  |  |  |  | 
6-7 | 6 | 6 | 12 | 7 |  |  |  |  | 
7-8 | 1 | 2 | 3 | 2 | 17 |  |  |  | 

## Slide 13
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 | 5 | 7 |  |  | 
2-5 | 3 | 4 | 5 | 4 | 5 | 9 |  |  | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 |  |  | 
4-5 | 1 | 2 | 3 | 2 | 7 | 9 |  |  | 
5-6 | 1 | 1 | 1 | 1 | 9 | 10 |  |  | 
6-7 | 6 | 6 | 12 | 7 | 10 | 17 |  |  | 
7-8 | 1 | 2 | 3 | 2 | 17 | 19 |  |  | 

## Slide 14
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 | 5 | 7 |  |  | 
2-5 | 3 | 4 | 5 | 4 | 5 | 9 |  |  | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 |  |  | 
4-5 | 1 | 2 | 3 | 2 | 7 | 9 |  |  | 
5-6 | 1 | 1 | 1 | 1 | 9 | 10 |  |  | 
6-7 | 6 | 6 | 12 | 7 | 10 | 17 |  |  | 
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0

## Slide 15
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 |  |  | 
2-4 | 2 | 2 | 2 | 2 | 5 | 7 |  |  | 
2-5 | 3 | 4 | 5 | 4 | 5 | 9 |  |  | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 |  |  | 
4-5 | 1 | 2 | 3 | 2 | 7 | 9 |  |  | 
5-6 | 1 | 1 | 1 | 1 | 9 | 10 |  |  | 
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0

## Slide 16
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2 | 4 | 5 | 6 | 5 | 0 | 5 |  |  | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0

## Slide 17
Solution
1
3
2
5
4
1
5
9
6
4
2
3
8
7
7
2
2
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf
 | to | tm | tp |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0

## Slide 18
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf | S
 | to | tm | tp |  |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0 | 
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5 | 
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0 | 
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0 | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5 | 
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0 | 
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0 | 
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0 | 
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0 | 
Solution

## Slide 19
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf | S
 | to | tm | tp |  |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0 | 1/3
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5 | 
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0 | 
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0 | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5 | 
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0 | 
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0 | 
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0 | 
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0 | 
Solution

## Slide 20
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf | S
 | to | tm | tp |  |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0 | 1/3
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5 | 
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0 | 0
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0 | 
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5 | 
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0 | 
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0 | 
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0 | 
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0 | 
Solution

## Slide 21
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf | S
 | to | tm | tp |  |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0 | 1/3
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5 | 
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0 | 0
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0 | 1/3
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5 | 
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0 | 1/3
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0 | 0
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0 | 1
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0 | 1/3
Solution

## Slide 22
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf | S
 | to | tm | tp |  |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0 | 1/3
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5 | 
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0 | 0
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0 | 1/3
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5 | 
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0 | 1/3
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0 | 0
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0 | 1
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0 | 1/3
Solution

## Slide 23
Activity | Duration (week) |  |  | te | Es | Ef | Ls | Lf | Tf | S
 | to | tm | tp |  |  |  |  |  |  | 
1-2* | 4 | 5 | 6 | 5 | 0 | 5 | 0 | 5 | 0 | 1/3
1-3 | 1 | 3 | 5 | 3 | 0 | 3 | 5 | 8 | 5 | 
2-4* | 2 | 2 | 2 | 2 | 5 | 7 | 5 | 7 | 0 | 0
2-5* | 3 | 4 | 5 | 4 | 5 | 9 | 5 | 9 | 0 | 1/3
3-7 | 7 | 8 | 15 | 9 | 3 | 12 | 8 | 17 | 5 | 
4-5* | 1 | 2 | 3 | 2 | 7 | 9 | 7 | 9 | 0 | 1/3
5-6* | 1 | 1 | 1 | 1 | 9 | 10 | 9 | 10 | 0 | 0
6-7* | 6 | 6 | 12 | 7 | 10 | 17 | 10 | 17 | 0 | 1
7-8* | 1 | 2 | 3 | 2 | 17 | 19 | 17 | 19 | 0 | 1/3
Solution